## Slide 1
Transition Plan - Decisions

## Slide 2
Customer Care
DHI Current Architecture
Orders
Microsoft Dynamics
Maconomy
Sales App (CPQ) + SMA + Config IT
Internet
License Server
MIKE

## Slide 3
Onboarding and New Product Training for FlexNet Operations ALM
  Standard training
  3rd Party License Technology Assistance
Product Definition Assistance in FNO for DHI products.
Import of some Entitlement data.
Integration Assistance from Maconomy to FNO
  New Order
  SMA Renewal
Assistance using Java callout to support current DHI license generation
Assistance with flow to send data to DHI Internet License Server using new API
FNO data back to Dynamics
Go Live Target August 2025
Phase 1 Scope
This is the list of agreed on scope for the back office development for DHI

## Slide 4
Timeline
Project Kickoff
FNO Back Office
Training
(2 weeks)
UAT Configuration
Customer License Key Generator
BackOffice Integration
(4 weeks)
PROD Deployment
Customer License Key Generator
BackOffice Integration
(2 weeks)
System Testing
PROD Validation
Go Live!
Postproduction Support
(30 days)
UAT Configuration
Customer License Key Generator
BackOffice Integration
(4 weeks)
PROD Deployment
Provisioning Internet License Server BackOffice Integration
(2 weeks)
UAT Configuration
Customer License Key Generator
BackOffice Integration
(2 weeks)
Entitlement Data Imports
UAT Validation (2 weeks)
January
February
March
May
DHI Phase 1 Proposed Timeline
Remaining Release Cycle 2024-2025 |  |  |  | 
Month | December | January | February | March
UAT Release Cycle | 25-Nov | TBD | TBD | TBD
PROD Release Cycle | 10-Dec | TBD | TBD | TBD
July
April
June
August
September

## Slide 5
Customer Care
DHI Phase 1 Architecture
Orders
Microsoft Dynamics
Maconomy
Sales App (CPQ) + SMA
Internet
License Server
DHI
Revenera
FlexNet
Operations
DHI Key Gen
Java
Callout
MIKE

## Slide 6
Product Definition Assistance in FNO for DHI products
DHI will need to provide a list of all sellable items that can or have been sold during the legacy support window. (Estimated 5 years)
DHI will need to provide a table associating the sellable products to specific “feature” names that would appear in the license file.
DHI will need to provide a table of part numbers (SKU’s) that associate to these sellable products.
DHI will need to provide a representative sample of license files for these products

## Slide 7
Entitlement Data Migration
DECISION – DHI will need to define the window of time from which entitlement data will still be relevant for product and support renewals once the system of record used during renewals is FNO.
DHI will need to provide an export of these orders/entitlements
  Specifics around formatting of this data will be part of the project

## Slide 8
Integration Assistance from Maconomy to FNO
ASSUMPTION – DHI will use existing in-house resources to integrate Maconomy with FNO
DHI to focus on Maconomy side
Revenera to focus on FNO side
Modular to facilitate any future move away from Maconomy
Alpha needs to be complete by end of April 2025
Anticipate only testing & minor fixes June-July

## Slide 9
License Key File Generation
ASSUMPTION – Revenera to host key generator in production
Java Call-Out to be coded by Revenera based on information from DHI
DHI to provide license signing application details
Prototype completion target end of Q1 2025

## Slide 10
Support for sending new licenses to Internet License Server
Determine all use cases
  New License
  Updated License
DHI to provide API definition to Revenera
Target end of May 2025

## Slide 11
Additional Integration Work
Revenera to support DHI implementing an integration of data from FNO to Dynamics

## Slide 12
Customer Care
DHI Phase 2 Architecture
Orders
Microsoft Dynamics
Maconomy
Sales App (CPQ) + SMA
DHI
Revenera
FlexNet
Operations
MIKE
FNE
CLS

## Slide 13
Timeline
Project Kickoff
Design Workshops
(1 weeks)
FNE Training
(1 week)
CLL Proliferation
(4 weeks)
Production Setup for FNE Products
(2 weeks)
Data Analytics Support, Prod Validation
(2 weeks)
FE FLOW Pilot Testing, UAT Validation, License Manager
(4 weeks)
Assistance with Common License Layer (CLL)
(4 weeks)
FNE and New Product Integration Assistance in UAT
(2 weeks)
Ongoing Assistance as Needed
(2 weeks)
January
February
March
May
DHI FNE Adoption Proposed Timeline (Phase 2)
July
April
June
August
September
Testing

## Slide 14
Phase 2 Scope
Provide Training for DHI
  FNE for Developers
  FNO and FNE for Customer Care and Technical Support
Assist with the design of how FNE will be used for DHI products
Assist DHI engineering adding FNE to FEFLOW in a Prototype/Beta/Production sequence through 2025
Assist DHI in creating a Common License Layer in conjunction with FEFLOW work
Provide Technical Assistance for Adding CLL to all other DHI products
Provide Technical Assistance for DHI to Implement/Update License Manager Application
Provide Technical Assistance for DHI to Use Snowflake or FNO Data Extracts to Populate Data Warehouse
Provide Technical Assistance for DHI to Update the Web Portal/Self-Service User Experience Augmented with FNO
Provide Technical Assistance for DHI to Update MIKE Cloud to use CMAPI or FlexNet Embedded to support the Cloud Hybrid Model
Assist DHI in Defining Installation Archive
Go Live Target November 2025

## Slide 15
Assist with the design of how FNE will be used for DHI products
Determine how best to support DHI’s “Glass Wall” concept with existing FNO/FNE/CLS functionality
Define workflows for license acquisition and return
  Online
  Offline
Define workflows for license use in-product
Identify FNE API’s and sequence for common license control layer

## Slide 16
Assist DHI engineering adding FNE to FEFLOW
Prototype/Beta/Production sequence through 2025
  Prototype – Target April 2025
  Beta – Target Summer 2025
  Production – Target Nov 2025
Support DHI to standardize implementation to be reusable across all DHI products
  Common License Layer (CLL)
Support QA testing

## Slide 17
Provide Technical Assistance
Adding CLL to all other DHI products
DHI to Implement/Update License Manager Application
  DHI to provide details of all supported workflows
  Revenera to assist with design of updates
DHI to Use Snowflake or FNO Data Extracts to Populate Data Warehouse
  Revenera to provide training and technical support
Update the Web Portal/Self-Service User Experience Augmented with FNO
  DHI to provide details of all supported workflows
  Revenera to assist with design of updates

## Slide 18
Provide Technical Assistance (continued)
DHI to Update MIKE Cloud to use CMAPI or FlexNet Embedded to support the Cloud Hybrid Model
Revenera to assist DHI in defining Installation Archive